## Sheet1
# | date | work | detail | time planned | time spent
1 | 2024-11-04 | testing new PS2 remote with sample code. | testing for remote working | 2 | 1.5
2 | 2024-11-05 | coding : receive button press-API | retrieve | 2 | 2
3 | 2024-11-19 | coding : 3 motors fwd-rvs working with no speed control | coding | 8 | 6
4 | 2024-11-20 | coding and wiring for speed control+ test | work | 2 | 3
[5 empty] | 12.5 | 600 | 7500